## Sheet1
ID | WBS | Task Name | Iteration
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | 1 | Project | bar: Iteration 1 to Iteration 9
2 | 1.1 | Pre-Project
3 | 1.1.1 | Research
4 | 1.1.1.1 | Mobile Development
5 | 1.1.1.2 | Implementation
6 | 1.1.1.3 | RESTful Web Services
7 | 1.1.2 | Project Setup | bar: Iteration 2 to Iteration 8
8 | 1.1.2.1 | Software
9 | 1.1.2.2 | Web Server for Web Services
10 | 1.1.2.3 | Database
11 | 1.1.2.4 | Obtain Licenses
12 | 1.1.3 | Brainstorm Ideas
13 | 1.1.3.1 | Choose App Idea
14 | 1.1.3.2 | App Research
15 | 1.1.3.3 | Marketplace Need
16 | 1.2 | Inception | bar: Iteration 2 to Iteration 9
17 | 1.2.1 | Vision And Scope Document | bar: Iteration 2 to Iteration 9
18 | 1.2.2 | System Scope | bar: Iteration 2 to Iteration 9
19 | 1.2.3 | Risks | bar: Iteration 2 to Iteration 9
20 | 1.2.4 | Work Breakdown Structure | bar: Iteration 2 to Iteration 9
75 | 1.2.5 | Setup Website Documentation
21 | 1.3 | Design | bar: Iteration 2 to Iteration 9
22 | 1.3.1 | System Design
23 | 1.3.2 | Database
24 | 1.3.2.1 | ERD
25 | 1.3.2.2 | Structure
26 | 1.3.2.3 | Tables
27 | 1.3.3 | Web Services
28 | 1.3.3.1 | Structure
29 | 1.3.3.2 | Diagram
30 | 1.3.4 | Phone Development | bar: Iteration 2 to Iteration 8
31 | 1.3.4.1 | Class Diagram | bar: Iteration 2 to Iteration 8
32 | 1.3.4.2 | Design Pattern | bar: Iteration 2 to Iteration 8
33 | 1.4 | Development | bar: Iteration 2 to Iteration 8
34 | 1.4.1 | Database | bar: Iteration 2 to Iteration 8
35 | 1.4.1.1 | Create Tables | bar: Iteration 2 to Iteration 8
36 | 1.4.1.2 | Implement SQL | bar: Iteration 2 to Iteration 8
37 | 1.4.2 | Web Services | bar: Iteration 2 to Iteration 8
38 | 1.4.2.1 | Implement | bar: Iteration 2 to Iteration 8
39 | 1.4.3 | Administrator Website | bar: Iteration 2 to Iteration 8
40 | 1.4.3.1 | Classes | bar: Iteration 2 to Iteration 8
41 | 1.4.3.2 | Code-Behind | bar: Iteration 2 to Iteration 8
42 | 1.4.3.3 | User Interface | bar: Iteration 2 to Iteration 8
43 | 1.4.4 | Phone Application | bar: Iteration 2 to Iteration 8
44 | 1.4.4.1 | Back-End Code | bar: Iteration 2 to Iteration 8
45 | 1.4.4.2 | User Interface and Hookup | bar: Iteration 2 to Iteration 8
46 | 1.4.4.2.1 | Windows Phone | bar: Iteration 2 to Iteration 8
47 | 1.4.4.2.2 | Android | bar: Iteration 2 to Iteration 8
48 | 1.4.4.2.3 | iOS | bar: Iteration 2 to Iteration 8
49 | 1.5 | Testing | bar: Iteration 2 to Iteration 8
50 | 1.5.1 | Database | bar: Iteration 2 to Iteration 8
51 | 1.5.1.1 | Data Stored Correctly | bar: Iteration 2 to Iteration 8
52 | 1.5.1.2 | Data Integrety | bar: Iteration 2 to Iteration 8
53 | 1.5.1.3 | Performance | bar: Iteration 2 to Iteration 8
54 | 1.5.2 | Web Services | bar: Iteration 2 to Iteration 8
55 | 1.5.2.1 | Set Up Correctly | bar: Iteration 2 to Iteration 8
56 | 1.5.2.2 | Expected Logic | bar: Iteration 2 to Iteration 8
57 | 1.5.2.3 | Performance | bar: Iteration 2 to Iteration 8
58 | 1.5.3 | Administrator Website | bar: Iteration 2 to Iteration 8
59 | 1.5.3.1 | Hooked up with Web Services Correctly | bar: Iteration 2 to Iteration 8
60 | 1.5.3.2 | Validate Data Input | bar: Iteration 2 to Iteration 8
61 | 1.5.3.3 | Performance | bar: Iteration 2 to Iteration 8
62 | 1.5.4 | Phones | bar: Iteration 2 to Iteration 8
63 | 1.5.4.1 | Back-End Logic Correct | bar: Iteration 2 to Iteration 8
64 | 1.5.4.2 | Hooked up with Web Services Correctly | bar: Iteration 2 to Iteration 8
65 | 1.5.4.3 | Handle Data Effectively | bar: Iteration 2 to Iteration 8
66 | 1.5.4.4 | Performance | bar: Iteration 2 to Iteration 8
67 | 1.5.4.5 | Effective UI / Self Intuitive | bar: Iteration 2 to Iteration 8
68 | 1.5.4.6 | Data Validation | bar: Iteration 2 to Iteration 8
69 | 1.6 | Release | bar: Iteration 2 to Iteration 8
70 | 1.6.1 | Effective Deployement | bar: Iteration 2 to Iteration 8
71 | 1.6.2 | Deployed Successfully to Stores | bar: Iteration 2 to Iteration 8
72 | 1.7 | Maintainence | bar: Iteration 2 to Iteration 8
73 | 1.7.1 | Bug Fixes | bar: Iteration 2 to Iteration 8
74 | 1.7.2 | Feature Updates | bar: Iteration 2 to Iteration 8