## Sheet1
ID | WBS | Task Name | Iteration
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | 1 | Project | bar: Iteration 1
2 | 1.1 | Pre-Project | bar: Iteration 1
3 | 1.1.1 | Research | bar: Iteration 8
4 | 1.1.1.1 | Mobile Development
5 | 1.1.1.2 | Implementation | bar: Iteration 1
6 | 1.1.1.3 | RESTful Web Services | bar: Iteration 3
7 | 1.1.2 | Project Setup | bar: Iteration 1
8 | 1.1.2.1 | Software | bar: Iteration 1
9 | 1.1.2.2 | Web Server for Web Services | bar: Iteration 1
10 | 1.1.2.3 | Database | bar: Iteration 1
11 | 1.1.2.4 | Obtain Licenses | bar: Iteration 8
12 | 1.1.3 | Brainstorm Ideas | bar: Iteration 1
13 | 1.1.3.1 | Choose App Idea | bar: Iteration 1
14 | 1.1.3.2 | App Research | bar: Iteration 1
15 | 1.1.3.3 | Marketplace Need | bar: Iteration 1
16 | 1.2 | Inception | bar: Iteration 1
17 | 1.2.1 | Vision And Scope Document | bar: Iteration 1
18 | 1.2.2 | System Scope | bar: Iteration 2
19 | 1.2.3 | Risks | bar: Iteration 2
20 | 1.2.4 | Work Breakdown Structure
75 | 1.2.5 | Setup Website Documentation | bar: Iteration 2
76 | 1.2.6 | Test Plan | bar: Iteration 18
77 | 1.2.7 | User Expereince Guide | bar: Iteration 18
78 | 1.2.8 | User Manuals | bar: Iteration 18
79 | 1.2.9 | Developer Guide | bar: Iteration 18
21 | 1.3 | Design | bar: Iteration 2
22 | 1.3.1 | Overall System | bar: Iteration 2
23 | 1.3.2 | Database | bar: Iteration 4
24 | 1.3.2.1 | ERD | bar: Iteration 4
25 | 1.3.2.2 | Structure | bar: Iteration 2
26 | 1.3.2.3 | Tables | bar: Iteration 2
27 | 1.3.3 | Web Services | bar: Iteration 3
28 | 1.3.3.1 | Structure | bar: Iteration 3
29 | 1.3.3.2 | Diagram | bar: Iteration 3
30 | 1.3.4 | Phone Development | bar: Iteration 8
31 | 1.3.4.1 | Class Diagram | bar: Iteration 8
32 | 1.3.4.2 | Design Pattern | bar: Iteration 8
33 | 1.4 | Development | bar: Iteration 2
34 | 1.4.1 | Database | bar: Iteration 2
35 | 1.4.1.1 | Create Tables | bar: Iteration 2
36 | 1.4.1.2 | Implement SQL | bar: Iteration 2
37 | 1.4.2 | Web Services | bar: Iteration 4 to Iteration 5
38 | 1.4.2.1 | Implement | bar: Iteration 4 to Iteration 5
39 | 1.4.3 | Administrator Website | bar: Iteration 6
40 | 1.4.3.1 | Classes | bar: Iteration 6
41 | 1.4.3.2 | Code-Behind | bar: Iteration 6
42 | 1.4.3.3 | User Interface | bar: Iteration 6
43 | 1.4.4 | Phone Application | bar: Iteration 10
44 | 1.4.4.1 | Binding Code | bar: Iteration 13
45 | 1.4.4.2 | User Interface and Hookup | bar: Iteration 13
46 | 1.4.4.2.1 | Windows Phone | bar: Iteration 13
47 | 1.4.4.2.2 | Android | bar: Iteration 14
48 | 1.4.4.2.3 | iOS
93 | 1.4.5 | PCL | bar: Iteration 9
94 | 1.4.5.1 | Classes | bar: Iteration 11
95 | 1.4.5.2 | View Models | bar: Iteration 11
96 | 1.4.5.3 | Async for Web Services | bar: Iteration 11
49 | 1.5 | Testing | bar: Iteration 11
80 | 1.5.1 | Integration Testing
81 | 1.5.1.1 | Web Service To Database | bar: Iteration 5
82 | 1.5.1.2 | Admin CMS to Web Services | bar: Iteration 7
83 | 1.5.1.3 | Web Services to Web Driver | bar: Iteration 17
84 | 1.5.1.4 | PCL to Web Services | bar: Iteration 11
85 | 1.5.1.5 | Windows Phone to PCL | bar: Iteration 12
86 | 1.5.1.6 | Android Phone to PCL | bar: Iteration 10
87 | 1.5.2 | Performance Testing | bar: Iteration 16
88 | 1.5.2.1 | Database Connections | bar: Iteration 16
89 | 1.5.2.2 | Recursive Database Calls | bar: Iteration 16
90 | 1.5.2.3 | Web Service Response Time | bar: Iteration 16
91 | 1.5.2.4 | Web Service JSON File Size | bar: Iteration 16
92 | 1.5.2.5 | PCL Async Response Time | bar: Iteration 16
50 | 1.5.3 | Database | bar: Iteration 2
51 | 1.5.3.1 | Data Stored Correctly | bar: Iteration 9; Iteration 14
52 | 1.5.3.2 | Data Integrety | bar: Iteration 9; Iteration 14
54 | 1.5.4 | Web Services | bar: Iteration 4
55 | 1.5.4.1 | Set Up Correctly | bar: Iteration 4
56 | 1.5.4.2 | Expected Logic | bar: Iteration 4
58 | 1.5.5 | Administrator Website | bar: Iteration 6
60 | 1.5.5.1 | Validate Data Input
62 | 1.5.6 | Phones | bar: Iteration 10
63 | 1.5.6.1 | Back-End Logic Correct | bar: Iteration 16
65 | 1.5.6.2 | Handle Data Effectively | bar: Iteration 16
67 | 1.5.6.3 | Effective UI / Self Intuitive | bar: Iteration 13 to Iteration 14
68 | 1.5.6.4 | Data Validation
69 | 1.6 | Release
70 | 1.6.1 | Effective Deployement
71 | 1.6.2 | Deployed Successfully to Stores
72 | 1.7 | Maintainence
73 | 1.7.1 | Bug Fixes
74 | 1.7.2 | Feature Updates